## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US001 | As a developer, I want to set up the Python and LangChain environment, so that I can build and test LLM-based agents locally. | Must Have | Python and Langchain Installation | Backend Team | Completed
Sprint 1 | Sprint 1 | US002 | As an agent developer, I want to create a single agent with prompt templates so that it can respond to user queries via console. | Must Have | LLM Connection | Backend Team | Completed
Sprint 2 | Sprint 2 | US003 | As a developer, I want to integrate tools with error handling, so that the agent can perform certain tasks using tools. | Must Have | Base Agent | Backend Team | Completed
Sprint 3 | Sprint 3 | US004 | As a developer, I want to implement multi-agents with individual memory, so the work is divided logically. | Must Have | Tool enabled Agent | Backend Team | Completed
Sprint 3 | Sprint 3 | US005 | As a developer, I want to implement shared memory so that agents can reuse knowledge across sessions. | Should Have | Multi-agent setup | Backend Team | Completed
Sprint 4 | Sprint 4 | US006 | As a developer, I want to design a workflow using FAST API so that external system can trigger it. | Must Have | Orchestration Logic | Backend Team | Completed
Sprint 4 | Sprint 4 | US007 | As a front-end developer, I want to create a simple UI so that a user can interact easily. | Could Have | FAST API | Frontend Team | Completed

## Sprint Backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US001 | T1 | Install and set Python and LangChain enviornment | 17-11-2025 | 18-11-2025 | Backend Team | Environment Set up | Completed | 3 | bar: Day 1 to Day 2
US001 | T2 | Configure LLM API and test the connection | 19-11-2025 | 20-11-2025 | Backend Team | LLM Configuration | Completed | 3 | bar: Day 3 to Day 4
US002 | T3 | Create an agent with prompt template and verify the console output | 21-11-2025 | 23-11-2025 | Backend Team | Agent Creation | Completed | 6 | bar: Day 5 to Day 7
US003 | T4 | Integrate tools into agent | 26-11-2025 | 29-11-2025 | Backend Team | Tool integration | Completed | 7 | bar: Day 1 to Day 4
US003 | T5 | Implement error handling for tools | 29-12-2025 | 2025-02-12 | Backend Team | Error Handling | Completed | 5 | bar: Day 4 to Day 8
US004 | T6 | Implement multi-agent workflow with individual memory | 2025-10-12 | 16-12-2025 | Backend Team | Multi-agent development | Completed | 10 | bar: Day 1 to Day 7
US005 | T7 | Create Shared memory usable by all agents | 17-12-2025 | 23-12-2025 | Backend Team | Shared memory development | Completed | 8 | bar: Day 8 to Day 14
US006 | T8 | Develop REST API to trigger agent workflow | 24-12-2025 | 30-12-2025 | Backend Team | API development | Pending | -
US007 | T9 | Create simple UI to call agent via REST API | 31-12-2025 | 2026-06-01 | Frontend Team | UI development | Pending | -

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 3 | Initial confusion with LangChain abstractions | Referred official docs & simplified agent setup
Sprint 1 | Day 7 | Prompt responses inconsistent | Improved prompt templates
Sprint 2 | Day 4 | Tool invocation errors | Added clear tool descriptions & error handling
Sprint 2 | Day 8 | Agent not choosing tools correctly | Prompt tuning for tool usage
Sprint 3 | Day 5 | Memory not persisting correctly | Switched to VectorStore-based memory
Sprint 3 | Day 10 | Agent coordination delay | Optimized orchestration flow

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-11-12 | 2025-11-25 | Backend team | Studying LangChain fundamentals, agent concepts | Random experimentation without structure | Daily hands-on practice with small examples | Set up LangChain and built a basic single-agent prototype
2 | Sprint 2 | 2025-11-26 | 2025-12-09 | Backend team | Designing tools with clear input/output | Hardcoding logic inside agent | Writing reusable tools | Implemented reusable tools and integrated them with the agent
3 | Sprint 3 | 2025-12-10 | 2025-12-23 | Backend team | Defining clear agent roles | Mixing responsibilities across agents | Modular agent architecture | Created separate agents with clearly defined responsibilities